## Sheet1
Team: |  |  |  | Unit: person-hours
Sprint | User Story ID | User Story | Priority | Estimated Team Effort | Actual Team Effort | Done?
#1 | #1 | As a traveler, I want to book different rooms at different times, to ensure that I have a place to stay in the places I’m traveling to. | 20 | 10 | … | …
#1 | #2 | As a traveler, I want to be able to unbook my room, if something comes up before my stay. | 10 | 3
#1 | #3 | As a hotel manager, I want to list available rooms on different dates, to allow customers to order rooms. | 10 | 6
#1 | #4 | As a hotel manager, I want to be able to unlist a room once it has been booked, to prevent double booked rooms. | 10 | 1
#2 | #5 | As a post hotel guest, I want to leave a review of the hotel I stayed in, to warn people about the awful food there. | 30 | 4
#2 | #6 | As a possible guest, I want to see the reviews that have been left on the hotels, to help make a decision. | 30 | 3
#2 | #7 | As a post hotel guest, I want to be able to leave a rating on the hotel I stayed on, to help possible guests make their decision. | 20 | 2
#2 | #8 | As a user, I want to see the average rating of a hotel to help me decide which hotel to book | 20 | 1
#3 | #9 | As a user, I want to be able to see how many reviews and ratings a hotel has, to see if it is a popular hotel and thus help me make my decision. | 30 | 1
#2 | #10 | As a possible hotel guest, I want to narrow my search down to specific factors, to help me find a hotel that suits me. | 10 | 10
#3 | #11 | As a traveler, I would like to get some suggestions on transportation from the airport to the hotel, because I don’t know which means of transport is best in the country. | 50 | 8
#3 | #12 | As a travel company owner, I would like to list my buses, to provide dates and prices for customers. | 50 | 6
#1 | #13 | As a hotel owner, I would like to be able to list my hotel, to provide dates and prices for customers. | 10 | 3
#1 | #14 | As a hotel owner, I would like to be able to list my hotel, to provide dates and prices for customers. | 10 | 2